## Main Topics
Topic ID | Topic | Category | Start Date | Expected End Date | Actual End Date | Overall Status | Documentation | Sub-Topics Link
1000 | Basics of GenAI | AI/ML | 2025-11-04 | 2025-11-06 | 2025-11-06 | Completed | https://docs.google.com/document/d/1eFNvfXvnvg8zaVc7UnCYuoOeiRnccnxJzxsqXaaEkXQ/edit?usp=sharing | GO
2000 | Postgres, Pgadmin4 | DB | 2025-11-07 | 2025-11-11 | 2025-11-11 | Completed | https://docs.google.com/document/d/1eFNvfXvnvg8zaVc7UnCYuoOeiRnccnxJzxsqXaaEkXQ/edit?usp=sharing | GO
3000 | Docker | Containerisation | 2025-11-12 | 2025-11-24 | 2025-11-21 | Completed | https://docs.google.com/document/d/1HnhcFHjqWiHk4LkF_sZGLQpLyTqckk6zZYMqmtxf_dg/edit?usp=sharing | GO
4000 | FastAPI | Backend | 2025-11-14 | 2025-11-30 | 2025-11-26 | Completed | https://docs.google.com/document/d/1O89BV4dYKDRRb-bW7dL0vIlIBumCMC38KXVjpw7uQcw/edit?usp=sharing | GO
5000 | Git, Github | Version History | 2025-11-27 | 2025-12-04 |  | In Progress | https://docs.google.com/document/d/13SlpZbMJ52VxuuaGhp9Z7lY60it2GHCgS44sJsr6iWQ/edit?usp=sharing | GO
6000

## Sub Topics
Sub Topic ID | Sub-Topics | Parent Topic | Expected Start Date | Actual Start Date | Expected End Date | Actual End Date | Status | Resources Used
1001 | Foundations of AI & ML | Basics of GenAI | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | Completed | YouTube, ChatGPT, Web
1002 | Understanding GenAI | Basics of GenAI | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | Completed | YouTube, ChatGPT, Web
1003 | LLMs & Fine Tunings, Embeddings | Basics of GenAI | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | Completed | YouTube, ChatGPT, Web
1004 | Tools & Framework, Multimodal GenAI | Basics of GenAI | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | Completed | YouTube, ChatGPT, Web
2001 | postgres, Pgadmin4 installation | Postgres, Pgadmin4 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | Completed | ChatGPT, Web
2002 | Understanding Titan DB | Postgres, Pgadmin4 | 2025-11-07 | 2025-11-07 | 2025-11-10 | 2025-11-10 | Completed
2003 | Refresh SQL Queries | Postgres, Pgadmin4 | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-11 | Completed | ChatGPT, Web
3001 | Introduction | Docker | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | Completed | YouTube, ChatGPT, Web
3002 | Installation & Basics | Docker | 2025-11-12 | 2025-11-12 | 2025-11-13 | 2025-11-13 | Completed | ChatGPT, Web
3003 | Docker Images | Docker | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | Completed | YouTube
3004 | Dockerfile | Docker | 2025-11-18 | 2025-11-19 | 2025-11-18 | 2025-11-19 | Completed | Web
3005 | Working With Containers | Docker | 2025-11-19 | 2025-11-20 | 2025-11-19 | 2025-11-20 | Completed | Web
3006 | Docker Volumes | Docker | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | Completed | Web
3007 | Docker Networking | Docker | 2025-11-21 | 2025-11-20 | 2025-11-21 | 2025-11-21 | Completed | Web
3008 | Docker Compose | Docker | 2025-11-22 | 2025-11-20 | 2025-11-22 | 2025-11-20 | Completed | Web
3009 | Docker Registry | Docker | 2025-11-24 | 2025-11-18 | 2025-11-24 | 2025-11-18 | Completed | Web
4001 | Introduction | FastAPI | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | Completed | YouTube, Web
4002 | Installation & Setup | FastAPI | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | Completed | ChatGPT, Web
4003 | Basic API Endpoints | FastAPI | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | Completed | YouTube, Web
4004 | Pydantic Models | FastAPI | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | Completed | YouTube, Web
4005 | Dependency Injection | FastAPI | 2025-11-19 | 2025-11-18 | 2025-11-19 | 2025-11-18 | Completed | YouTube, Web
4006 | Path Operations | FastAPI | 2025-11-20 | 2025-11-21 | 2025-11-20 | 2025-11-21 | Completed | YouTube, ChatGPT, Web
4007 | Request Handling | FastAPI | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-22 | Completed | ChatGPT, Web
4008 | Error Handling | FastAPI | 2025-11-22 | 2025-11-22 | 2025-11-22 | 2025-11-22 | Completed | ChatGPT, Web
4009 | Authentication & Authorization | FastAPI | 2025-11-24 | 2025-11-24 | 2025-11-25 | 2025-11-24 | Completed | YouTube, ChatGPT, Web
4010 | Middleware | FastAPI | 2025-11-26 | 2025-11-24 | 2025-11-26 | 2025-11-24 | Completed | ChatGPT, Web
4011 | Database Integration | FastAPI | 2025-11-27 | 2025-11-25 | 2025-11-28 | 2025-11-25 | Completed | YouTube, ChatGPT, Web
4012 | Response Handling | FastAPI | 2025-11-29 | 2025-11-25 | 2025-11-29 | 2025-11-25 | Completed | ChatGPT, Web
4013 | Deployment | FastAPI | 2025-11-30 | 2025-11-26 | 2025-11-30 | 2025-11-26 | Completed | YouTube
5001 | Introduction | Git, Github | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | Completed | Web
5002 | Installation & Setup | Git, Github | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | Completed | Web
5003 | Git Basics | Git, Github | 2025-11-27 | 2025-11-28 | 2025-11-28 | 2025-11-28 | Completed | ChatGPT, Web
5004 | Working With Files | Git, Github | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-12-02 | Completed | Web
5005 | Git Ignore | Git, Github | 2025-11-28 | 2025-12-02 | 2025-11-28 | 2025-12-02 | Completed | Web
5006 | Working With Tags & Releases | Git, Github | 2025-11-28 | 2025-12-03 | 2025-12-01 | 2025-12-03 | Completed | Web
5007 | Branching | Git, Github | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-02 | Completed | Web
5008 | GitHub Basics | Git, Github | 2025-12-01 | 2025-12-01 | 2025-12-02 | 2025-12-01 | Completed | Web
5009 | Collaboration Basics | Git, Github | 2025-12-02 | 2025-12-04 | 2025-12-02 |  | In Progress | Web
5010 | Undoing Mistakes (Essential Safety Skills) | Git, Github | 2025-12-02 | 2025-12-02 | 2025-12-03 | 2025-12-03 | Completed | Web
5011 | Handling Merge Conflicts | Git, Github | 2025-12-03 | 2025-12-03 | 2025-12-04 | 2025-12-04 | Completed | Web
6001

## New Tools
Core | Pytorch 2.x, JAX
Agents | LangChain/Langgraph/DSPy
Memory | Pinecone, weaviate, qdrant
serving | vLLM/Ollama
spredsheet | quadratic ai